Part B-1

1. Excellence

  1. Quality and pertinence of the project’s research and innovation objectives (and the extent to which they are ambitious, and go beyond the state of the art)
Motivation: Active matter, denoting collections of actively moving particles, is an emerging subject of study at the interface between physics, chemistry and biology. Due to the energy injection at single particle scale, active matter is constantly driven out of equilibrium and behaves very differently from those well-understood equilibrium systems. Over the past three decades, we have seen rapid growth of interest and investigations into active matter systems across a broad range of length scales, from large animals to tissues and cells.1–4 The ways they self-organize, as evidenced in bird flocks, fish schools and bacterial swarms, are exhibiting new states of matter, which are strictly prohibited in equilibrium systems. In the presence of boundaries with complex geometries, active matter exhibits more exotic phenomena including wall accumulation, motion rectification, ratchet effect and upstream swimming. These phenomena not only pose new challenges to fundamental biology and ecology, but also imply world-changing applications in therapeutics and robotics.5,6
State of the art: Due to their non-equilibrium nature, active matter show rich phenomena in complex environments. One the one hand, confinement influences transport⁠8⁠, rheology9–12, pressure13⁠, spatial distribution14–16⁠ and collective motion17–28⁠ of active matter. Curved confining walls, which are ubiquitous in biological systems, show rich and intriguing confinement effect on active matter. Inspired by the collective motion of confined driven filaments18⁠, Woodhouse and Goldstein constructed a theoretical model, demonstrating that the combination of circular confinement and activity allows for the emergence of stable self-organized rotational streaming.21⁠ Such circular confinement was then realized by emulsions and elastomer chambers, where single vortical flows were observed.24,25,27⁠ Liu et al. recently showed intriguing oscillatory dynamics in a similar geometry.20⁠ Ravnik and Yeomans studied the dynamics of active nematics under cylindrical confinement using simulation based on continuum equations. They showed that the collective vortical flows not only emerge along the cylinder axis (as shown by Woodhouse and others), but also within the plane of the cylinder.23⁠ Fily and co-workers developed a statistical theory for non-aligning, non-interacting active particles to study spatial distributions under strong confinement. They showed that in such confinement, particle concentrations at boundaries were proportional to the local curvature.29⁠ Nikola and co-workers showed, using particle-based theory and simulation, that not only the collective motion, but also the shear stress exerted by active particles on confining walls was wall-dependent.13⁠ These works show that curved confining walls alter the behavior and macroscopic properties of active matter. In particular, the only key parameter of curved confinement, curvature, has been shown to play an important role in particle spatial distributions29⁠ and collective motions24⁠. On the other hand, complex-shape passive objects show intriguing persistent and directed motions in active baths, which can be used for the extraction of work.30–33⁠ Angelani and co-workers, using numerical simulations, showed that asymmetric gear-like objects spontaneously rotated in a directed way in active active baths, forming the concept of “micromotor” powered by active matter.32⁠ This idea was then realized in experiment in experimental30,31⁠ and theoretical grounds.33⁠
The interplay between complex environments and active matter suggests a possibility to control and engineer active matter by carefully designing the confinement structures. While many exotic phenomena under confinement have been demonstrated, further understanding requires systematic investigations with well controlled model systems. Therefore, we propose the following project, which, we believe, is a crucial step to bridge the gap between fundamental studies and real-life applications of active matter.
Objectives: We seek to understand the interaction between complex geometries and the behavior of active matter, using a controllable model experimental system. Specifically, we want to (i) understand how confinement geometries influence the fluctuations of spherical particles. Systematic understanding will be gained by investigating the relevant dynamical properties of passive objects that are subject to various confining geometries. In addition to this simplest scenario, we also seek to understand the behavior of complex-shape objects in confined active bath. In particular, we seek to (ii) understand how confining wall curvature influences the fluctuations of complex-shape particles and to (iii) understand self-assembly of complex-shape passive particles in confined active baths. We expect to observe novel self-assembly principles in the presence of active matter under confinement.
Methodology: Emulsions offer controllable and high throughput experimental systems for studying confinement effect. Recent progress in microcapillary device allow us to produce double emulsions with well controlled compositions and dimensions.34⁠ To achieve the objectives, we will build a model experimental system based on (double) emulsions, to systematically study the interplay between complex environments and active matter.
Figure 1: Double emulsions with swimming bacteria in the middle aqueous phase. (a, b) Double emulsions in a micro-capillary device, operating at different flow rates. (c, d) Collected double emulsions observed with a higher magnification.
To respond to objective (i) “understand how confinement geometries influence the fluctuations of spherical particles”, we will study the fluctuations of the inner droplets in oil/water/oil double emulsions with bacterial suspensions in its middle aqueous phase as the active bath (Fig.1). The double emulsion system naturally imposes the simplest form of curved confining walls: a spherical shell. The sizes of both outer and inner droplets can be controlled by operating the device at different flow rates, as demonstrated in Fig.1.
To respond to objective (ii) “understand how confining wall curvature influences the fluctuations of complex-shape particles”, we will use the emulsion systems as in (i), but replacing the inner droplets with complex-shape particles, such as XXX, and study its fluctuations under different confining curvatures. The complex-shape particles will be fabricated using the 3D nano-printer in ESPCI.
To respond to objective (iii) “understand self-assembly of complex-shape passive particles in confined active baths”, we will encapsulate multiple complex-shape particles into a droplet comprising active matter. We expect to observe novel self-assembly principles in the presence of active matter under confinement.
The motions of the inner droplet and other objects confined in emulsions are inherently 3D. Therefore, 3D microscopy is an experimental challenge in this project. There are two techniques for 3D microscopy hosted in ESPCI: (i) Lagrangian 3D Tracking System and (ii) tilted confocal microscope. The former is developed by Prof. Eric Clement’s lab at PMMH for studying how bacteria explore in 3D space. The need of this project will facilitate the development of the system for tracking more complex objects, in addition to bacteria. The latter is developed by XXX (need some information about the confocal). In addition, holographic microscopy, which I have worked with during PhD at the University of Minnesota in collaboration with Prof. Jiarong Hong, will also be a candidate method to achieve 3D imaging. (need a figure illustrating the 3 imaging techniques)
Expected outcome
Combining the microfluidic techniques and the advanced 3D microscopy, we expect to generate a complete set of fluctuation data (trajectories) of passive oil droplets in confined active bath of various confining curvature and active particle concentration. An automated 3D tracking system, incorporating artificial intelligence technology, will also be demonstrated. Fluctuations of non-spherical passive particles will be compared with spherical particles. Self-assembly of non-spherical particles in active matter will be demonstrated. These experimental data are expected to facilitate further development of the model, and eventually close the gap between theory and application.
  1. Soundness of the proposed methodology (including interdisciplinary approaches, consideration of the gender dimension and other diversity aspects if relevant for the research project, and the quality of open science practices, including sharing and management of research outputs and engagement of citizens, civil society and end users, where appropriate)

Overall methodology: Our proposed research aims to systematically study the dynamics of particles in swimming bacterial bath under different confining curvature. Taking advantage of the microfluidic double emulsion experimental system, we can access a wide range of the key parameter – curvature. To overcome the key experimental challenge, 3D imaging, we have three candidate methods (3D tracking, tilted confocal and holography) ready to be tested. These two advantages will enable us to systematically study how curvature influences the fluctuations of an active bath.
Integration of disciplines: This project is inherently interdisciplinary, since it requires combining expertise in: i) biochemistry and biophysics to produce bacterial suspensions with controlled properties, ii) hydrodynamics and statistical physics to study their collective motion, iii) microfluidics and surface chemistry to produce complex confining environments, iv) topology and geometry to analyze the patterns emerging in these constrained environments. I have a solid physical and biological background, as well as experimental skills to carry out this project. In addition, my experience in studying active matter under confinement ensures that I am able bring together the expertise from me and the suggested host to achieve the objectives of the proposed project.
Gender dimension and other diversity aspects: ?
Open science practices: Host softwares and algorithms and GitHub. Host data on open data repositories, like HEPData. Publish milestone works on pre-print database, like arXiv. Youtube videos.
Research data management: Data will be organized and uploaded to open repositories every month with a report describing the purpose and statistics of them. A separate document will be maintained to account for the status and evolution of the whole data set over time.
RESEARCH QUESTIONS Knowledge of confinement effect on active matter is of key importance to solve real-life challenges with active matter. A few investigations on the role of confining wall curvature were conducted: curvature-dependent pressure13,38⁠ and curvature-dependent boundary distribution24⁠ were studied theoretically and numerically; curvature-dependent flow coherence was studied with both experiment and a hydrodynamic model.24⁠ The fact that experimental data are very scarce has been limiting the advancement of the field. We identify two major problems that are limiting us from obtaining abundant experimental data: (i) the protocols of producing confined active matter are either tedious or less controlled; (ii) the inherent 3D motion poses challenges on conventional microscopy.
Our proposed research overcomes these limitations by: (i) introducing microcapillary devices to produce double emulsions with well-controlled geometries; (ii) state-of-the-art microscopy techniques to capture 3D motions. Equipped with these techniques, we set out to investigate the following research questions:
RQ1. What is the effective temperature of an active bath in the dilute limit, where particle-particle interactions are not important? Is it the same as in the bulk? Is it curvature-dependent?
RQ2. What is the effective temperature of an active bath in the dense limit, where particle-particle interactions are important and collective motion emerges? Is it the same as in the bulk? Is it curvature-dependent?
RQ3. What are the motions of non-spherical objects like in confined active bath? Would there be novel self-organization phenomena if several particles are put together? Microparticle shape has been shown to be very crucial in therapeutical applications (Refs 218, 219 in Ghosh 2020).
  1. Quality of the supervision, training and of the two-way transfer of knowledge between the researcher and the host

Two-way transfer of knowledge between the researcher and the host organisation
There is a great potential for transfer of knowledge between me, the host laboratories at the PMMH and Gulliver labs in ESPCI and our external collaborators at University of Chile. A post-doctoral stay under Prof. Eric Clement’s supervision will be a great opportunity to acquire new knowledge and to produce an interdisciplinary and impactful study.
The proposed research focuses on the behavior of active matter under confinement. My knowledge of studying the diffusion, rheology and collective motions of bacterial suspensions, combined with working experience of microfluidics, advanced microscopy and image analysis together aligns perfectly with the skill set needed for carry out the proposed research.
Additionally, I can share with the host a mutant strain of E. coli whose motility can be controlled by light. I genetically engineered the mutant strain during my PhD at the University of Minnesota, and I believe it can lead to a more versatile experimental system and more concrete outcome of this research project. I will also share holographic imaging technique with the host lab, which can be a candidate method for 3D imaging if other proposed methods do not work out.
The hosts, the Clement, Lindner and Lopez-Leon groups at ESPCI, form an ideal combination of knowledge and techniques that are necessary for conducting the proposed research. Prof. Eric Clement and his group are world leading experimentalists on the study of active fluids, with special expertise in the behavior of active particles in complex environments. His lab is equipped with the state-of-the-art Lagrangian 3D tracking system, which makes resolving 3D motions possible. Prof. Anke Lindner is an internationally acknowledged specialist in the interactions between anisotropic particles and flow. Her knowledge will be valuable, especially when we study the motion of non-spherical particles in active baths. Prof. Teresa Lopez-Leon is experienced in studying confined liquid crystals using microfluidic devices. She has the technique of producing double emulsions readily available for the proposed research. Her knowledge on confinement effect in general will provide new perspectives to understand the behavior of confined active matter.
Planned training activities for the researcher (scientific aspects, management organisation, horizontal and key transferable skills...)
...
1.4	Quality and appropriateness of the researcher’s professional experience, competences and skills

I obtained my PhD degree with my thesis entitled “Novel properties and collective phenomena of active fluids”. During my PhD from 2015 to 2021 under the supervision of Prof. Xiang Cheng at the University of Minnesota, I studied the diffusion, rheology and collective motion of active matter experimentally. During these investigations, I have acquired expertise of various experimental techniques, including confocal microscopy, microfluidics, genetic engineering, particle synthesis and image analysis. These studies have led to 3 publications in international peer reviewed journals, with additional papers under preparation.
The proposed research topic matches well with my experience and skill set. I will be able to quickly adapt my expertise to the new work environment. In the mean time, the supervision from world leading scientists and being able to use the state-of-the-art equipments will benefit my career development enormously.

2.	Impact

2.1	Credibility of the measures to enhance the career perspectives and employability of the researcher and contribution to his/her skills development
4 aspects: technical, mentoring, research and project management
By working with the proposed host research groups at PMMH and Gulliver in ESPCI on investigating into cutting-edge problems in the multidisciplinary field of active matter, I (the researcher) will develop skills in research techniques, communication, mentoring and project management.
During a postdoc stay in the proposed host, I will have access to many state-of-the-art equipments, such as Lagrangian 3D tracking system, tilted confocal microscope and 3D nano-printer.
2.2	Suitability and quality of the measures to maximise expected outcomes and impacts, as set out in the dissemination and exploitation plan, including communication activities
- conferences; outreach activities;
2.3. The magnitude and importance of the project’s contribution to the expected scientific, societal and economic impacts
- ...
3.	Quality and Efficiency of the Implementation

3.1	Quality and effectiveness of the work plan, assessment of risks and appropriateness of the effort assigned to work packages

Milestones	Description	Month
M1	Set up protocols of double emulsion generation, 3D imaging and data analysis	6
M2	Data acquisition and analysis	14
M3	Fabrication of anisotropic particles	17
M4	Acquiring self-assembly data of anisotropic particles in active bath	21

Work package number	1	Start month	1	End month	8
Work package title	Dilute temperature
Objectives	Measure the “effective temperature” of confined dilute active bath
Description	- Demonstrate the capabilities of the proposed methods: producing double emulsions with microfluidic device, recording 3D motion of inner droplets with Lagrangian 3D tracking system and confocal microscopy / - Set up an experimental protocol / - Collect inner droplet trajectory data in various curvatures / - Write programs to extract the trajectories from images
Methodology
Deliverables					Month
	D1.1	Conference – APS DFD meeting USA, November 2022
	D1.2
	D1.3

Work package number	2	Start month	6	End month	14
Work package title	Concentrated temperature
Objectives	Measure the “effective temperature” of confined concentrated active bath
Description	- Measure effective temperature at a range of different bacterial concentrations, spanning from random swimming to collective motion, at fixed geometry / - Collect inner droplet trajectory data in various geometries and concentrations to complete a “phase diagram”
Methodology
Deliverables					Month
	D2.1
	D2.2
	D2.3

Work package number	3	Start month	12	End month	24
Work package title	Complex-shape object
Objectives	Measure the dynamics of complex-shape particles in active bath
Description	- Fabricate complex-shape particles using 3D nano-printer / - Measure fluctuations of single complex-shape particles in active emulsion / - Investigate self-assembly of complex-shape particles in active emulsion
Methodology
Deliverables					Month
	D3.1
	D3.2
	D3.3

3.2	Quality and capacity of the host institutions and participating organisations, including hosting arrangements

Insert here text for your proposal

--------------------------------------- End of page count (max 10 pages) -------------------------------

Part B-2
(No overall page limit applied)

4.	CV of the researcher
Insert here text for your proposal

5.	Capacity of the Participating Organisation(s)

5.1 Template table: Overview of Participating Organisations

Organisation role	PIC	Legal Entity Short Name	Academic organisation / (Y/N)	Country	Name of Supervisor
Beneficiary
Associated partner linked to a beneficiary (if applicable)
Associated partner for outgoing phase (mandatory for GF)
Associated partner for secondment (optional)
Associated partner for non-academic placement (optional)
Other: ________

5.2 Template table: Capacity of the Participating Organisations

Choose one of: /  Beneficiary (compulsory) /  Associated partner linked to a beneficiary (if applicable) /  Associated partner for outgoing phase (compulsory for GF only) /  Associated partner for secondment (optional) /  Associated partner for non-academic placement (optional)
[Full name + Legal Entity Short Name + Country]
General description
Role and profile of supervisor
Key research facilities, Infrastructure and Equipment
Previous and current involvement in EU-funded research and training programmes/actions/projects

6.	Additional ethics information

Insert here text for your proposal
(NB: Only if you have additional information that could not be included in the ethics self-assessment)

7.	Additional information on security screening

Insert here text for your proposal
(NB: Only if you answered yes to one of the questions in the security issues table, with the exception of “Does this activity involved HE associated and/or third countries?”)

8.	Letter(s) of commitment from associated partners (host for outgoing phase of Global Fellowship or non-academic placement host)

Insert here text for your proposal

1.	Ramaswamy, S. The Mechanics and Statistics of Active Matter. Annu. Rev. Condens. Matter Phys. 1, 323–345 (2010).
2.	Marchetti, M. C. et al. Hydrodynamics of soft active matter. Rev. Mod. Phys. 85, 1143–1189 (2013).
3.	Bechinger, C. et al. Active particles in complex and crowded environments. Rev. Mod. Phys. 88, (2016).
4.	Ramaswamy, S. Active matter. J. Stat. Mech. Theory Exp. 2017, (2017).
5.	Ghosh, A., Xu, W., Gupta, N. & Gracias, D. H. Active matter therapeutics. Nano Today 31, (2020).
6.	Chvykov, P. et al. Low rattling: A predictive principle for self-organization in active collectives. Science (80-. ). 371, 90–95 (2021).
7.	Wu, X.-L. & Libchaber, A. Particle diffusion in a quasi-two-dimensional bacterial bath. Phys. Rev. Lett. 84, (2000).
8.	Hernandez-Ortiz, J. P., Stoltz, C. G. & Graham, M. D. Transport and collective dynamics in suspensions of confined swimming particles. Phys. Rev. Lett. 95, 204501 (2005).
9.	Słomka, J. & Dunkel, J. Geometry-dependent viscosity reduction in sheared active fluids. Phys. Rev. Fluids 2, 9–12 (2017).
10.	Alonso-Matilla, R., Ezhilan, B. & Saintillan, D. Microfluidic rheology of active particle suspensions: Kinetic theory. Biomicrofluidics 10, 18–26 (2016).
11.	Liu, Z., Zhang, K. & Cheng, X. Rheology of bacterial suspensions under confinement. Rheol. Acta 58, (2019).
12.	Martinez, V. A. et al. A combined rheometry and imaging study of viscosity reduction in bacterial suspensions. Proc. Natl. Acad. Sci. U. S. A. 117, 2326–2331 (2020).
13.	Nikola, N. et al. Active Particles with Soft and Curved Walls: Equation of State, Ratchets, and Instabilities. Phys. Rev. Lett. 117, 1–5 (2016).
14.	Tailleur, J. & Cates, M. E. Sedimentation, trapping, and rectification of dilute bacteria. Epl 86, 60002 (2009).
15.	Caprini, L. & Marconi, U. M. B. Active chiral particles under confinement: Surface currents and bulk accumulation phenomena. Soft Matter 15, 2627–2637 (2019).
16.	Leoni, M. et al. Surfing and crawling macroscopic active particles under strong confinement: Inertial dynamics. Phys. Rev. Res. 2, 43299 (2020).
17.	Kudrolli, A., Lumay, G., Volfson, D. & Tsimring, L. S. Swarming and swirling in self-propelled polar granular rods. Phys. Rev. Lett. 100, 2–5 (2008).
18.	Schaller, V., Weber, C., Semmrich, C., Frey, E. & Bausch, A. R. Polar patterns of driven filaments. Nature 467, 73–77 (2010).
19.	Liu, P. et al. Oscillating collective motion of active rotors in confinement. Proc. Natl. Acad. Sci. U. S. A. 117, (2020).
20.	Liu, S., Shankar, S., Marchetti, M. C. & Wu, Y. Viscoelastic control of spatiotemporal order in bacterial active matter. Nature 590, 80–84 (2021).
21.	Woodhouse, F. G. & Goldstein, R. E. Spontaneous circulation of confined active suspensions. Phys. Rev. Lett. 109, (2012).
22.	Schaller, V. & Bausch, A. R. Topological defects and density fluctuations in collectively moving systems. Proc. Natl. Acad. Sci. U. S. A. 110, 4488–4493 (2013).
23.	Ravnik, M. & Yeomans, J. M. Confined active nematic flow in cylindrical capillaries. Phys. Rev. Lett. 110, 1–5 (2013).
24.	Wioland, H., Woodhouse, F. G., Dunkel, J., Kessler, J. O. & Goldstein, R. E. Confinement stabilizes a bacterial suspension into a spiral vortex. Phys. Rev. Lett. 110, 1–5 (2013).
25.	Lushi, E., Wioland, H. & Goldstein, R. E. Fluid flows created by swimming bacteria drive self-organization in confined suspensions. Proc. Natl. Acad. Sci. U. S. A. 111, 9733–9738 (2014).
26.	Wioland, H., Lushi, E. & Goldstein, R. E. Directed collective motion of bacteria under channel confinement. New J. Phys. 18, (2016).
27.	Wioland, H., Woodhouse, F. G., Dunkel, J. & Goldstein, R. E. Ferromagnetic and antiferromagnetic order in bacterial vortex lattices. Nat. Phys. 12, 341–345 (2016).
28.	Wu, K. T. et al. Transition from turbulent to coherent flows in confined three-dimensional active fluids. Science (80-. ). 355, (2017).
29.	Fily, Y., Baskaran, A. & Hagan, M. F. Dynamics of self-propelled particles under strong confinement. Soft Matter 10, 5609–5617 (2014).
30.	Di Leonardo, R. et al. Bacterial ratchet motors. Proc. Natl. Acad. Sci. U. S. A. 107, 9541–9545 (2010).
31.	Sokolov, A., Apodaca, M. M., Grzybowski, B. A. & Aranson, I. S. Swimming bacteria power microscopic gears. Proc. Natl. Acad. Sci. U. S. A. 107, 969–974 (2010).
32.	Angelani, L., Di Leonardo, R. & Ruocco, G. Self-starting micromotors in a bacterial bath. Phys. Rev. Lett. 102, 1–4 (2009).
33.	Pietzonka, P., Fodor, É., Lohrmann, C., Cates, M. E. & Seifert, U. Autonomous Engines Driven by Active Matter: Energetics and Design Principles. Phys. Rev. X 9, 41032 (2019).
34.	Lopez-Leon, T., Koning, V., Devaiah, K. B. S., Vitelli, V. & Fernandez-Nieves, A. Frustrated nematic order in spherical geometries. Nat. Phys. 7, 391–394 (2011).
35.	Utada, A. S. et al. Monodisperse double emulsions generated from a microcapillary device. Science (80-. ). 308, 537–541 (2005).
36.	Utada, A. S. et al. Dripping, jetting, drops, and wetting: The magic of microfluidics. MRS Bull. 32, 702–708 (2007).
37.	Darnige, T., Figueroa-Morales, N., Bohec, P., Lindner, A. & Clément, E. Lagrangian 3D tracking of fluorescent microscopic objects in motion. Rev. Sci. Instrum. 88, 055106 (2017).
38.	Solon, A. P. et al. Pressure is not a state function for generic active fluids. Nat. Phys. 11, 673–678 (2015).